## Sprint 1_Bug Report
Bug ID | Bug ID Number | Bug01_S2_TC_S2_017
| Reporter Name | Frances Liu | [5 empty] | Screenshots:
| Submitted Date | 2025/Sep/02
| Assigned Developer | Bowang Ding
Bug Overview | Summary | Duplicate students can be added to Course Offerings
| URL | https://localhost:7003/Admin/Course/CourseOffering
| Screenshots | See the right.
Bug Details | Steps to Reproduce | 1. Select role: admin 2. Enter the username:admin 3. Enter the password:admin 4. Click on log in 5. Click Manage Courses 6. Click Course Offerings 7. Click a course in the list: Software Testing 8. Click Upload Excel 9. Click choose file (a file with students list that two students have the same information) 10. Click upload and import
| Expected Results | Duplicated students should not been added to the course or only one data can be added.
| Observed Results | Duplicate students were added to Software Testing in Course Offerings
Prioritization | Bug Severity | Blocker | Critical | Major | Normal | Minor | Trivial
√
| Bug Priority | Top | High | Medium | Low | None
√
Environment | Device | Laptop
| Operating System | Windows
| Browser | Google Chrome
| File | See the files in folder "test data for Course Offerings"
Bug Track | Developer Response | duplicate data in the file has not been filtered
Fix Result | By Developer | Fixed | Not Bug
√
Retesting | Pass/Fail | Pass
Bug ID | Bug ID Number | Bug02_S2_TC_S2_029
| Reporter Name | Frances Liu | [5 empty] | Screenshots:
| Submitted Date | 2025/Sep/02
| Assigned Developer | Bowang Ding
Bug Overview | Summary | Some course can be deleted successfully, but some cannot. It showed error message but not sure to to delete successfully.
| URL | https://localhost:7003/Admin/Course/CourseOffering
| Screenshots | See the right.
Bug Details | Steps to Reproduce | 1. Select role: admin 2. Enter the username:admin 3. Enter the password:admin 4. Click on log in 5. Click Manage Courses 6. Click Course Offerings 7. Click a course in the list: Software Engineering 8. Click the button beside course Implementing Networks 9. Click delete 10. Click confirm
| Expected Results | A confirmation dialog should be displayed. The course should be deleted from the list. A success message should be diaplayed.
| Observed Results | An error message was displayed, the course was not deleted.
Prioritization | Bug Severity | Blocker | Critical | Major | Normal | Minor | Trivial
√
| Bug Priority | Top | High | Medium | Low | None
√
Environment | Device | Laptop
| Operating System | Windows
| Browser | Google Chrome
| File | No
Bug Track | Developer Response | courseoffering's related data has not been deleted
Fix Result | By Developer | Fixed | Not Bug
√
Retesting | Pass/Fail | Pass
Bug ID | Bug ID Number | Bug02_S3_TC_S2_029
| Reporter Name | Frances Liu | [5 empty] | Screenshots:
| Submitted Date | 2025/Sep/02
| Assigned Developer | Bowang Ding
Bug Overview | Summary | The assessment cannot be deleted successfully.
| URL | https://localhost:7003/Admin/Course/CourseOffering
| Screenshots | See the right.
Bug Details | Steps to Reproduce | 1. Select role: admin 2. Enter the username:admin 3. Enter the password:admin 4. Click on log in 5. Click Manage Assessments 6. Click Social Data Analytics 7. Select A1 8. Click delete 9. Click confirm
| Expected Results | A succcess message should be displayed. The data should be deleted in the assessment list.
| Observed Results | The assessment cannot be deleted. An error message was displayed.
Prioritization | Bug Severity | Blocker | Critical | Major | Normal | Minor | Trivial
√
| Bug Priority | Top | High | Medium | Low | None
√
Environment | Device | Laptop
| Operating System | Windows
| Browser | Google Chrome
| File | No
Bug Track | Developer Response | assessment's related data has not been deleted
Fix Result | By Developer | Fixed | Not Bug
√
Retesting | Pass/Fail | Pass