## Sheet1
Requirement Traceability Matrix (RTM)
Project Name: Learning Outcomes Tracking Application (LOTA)
Sprint | Requirement ID | Requirement Description | Test Case IDs/Groups | Status
Sprint 1 | R001 | Admin should be able to add new course information. | TC_S1_143 - TC_S1_154 TC_S1_160 - TC_S1_164 | Passed
| R002 | Admin should be able to update course information. | TC_S1_155 - TC_S1_159 | Passed
| R003 | Admin should be able to delete course information. | TC_S1_154, TC_S1_183 | Passed
| R004 | Admin should be able to add new tutor information. | TC_S1_082, TC_S1_104 | Passed
| R005 | Admin should be able to update tutor information. | TC_S1_105-TC_S1_120 | Passed
| R006 | Admin should be able to delete tutor information. | TC_S1_121-TC_S1_122 | Passed
| R007 | Admin should be able to add new student information. | TC_S1_030 - TC_S1_048 TC_S1_059 - TC_S1_068 | Passed
| R008 | Admin should be able to update student information. | TC_S1_049 - TC_S1_055 | Passed
| R009 | Admin should be able to delete student information. | TC_S1_056 - TC_S1_058 TC_S1_069 - TC_S1_071 | Passed
| R010 | Amin should be able to view tutor information. | TC_S1_073 | Passed
| R011 | Amin should be able to view course information. | TC_S1_138 - TC_S1_142 | Passed
| R012 | Amin should be able to view student information. | TC_S1_029 | Passed
| R013 | Admin should be able to view qualification information. | TC_S1_179 - TC_S1_181 TC_S1_185 - TC_S1_188 | Passed
| R014 | Admin should be able to add qualification information. | TC_S1_165 - TC_S1_171 | Passed
| R015 | Admin should be able to edit qualification information. | TC_S1_172 - TC_S1_175 | Passed
| R016 | Admin should be able to delete qualification information. | TC_S1_176 - TC_S1_178 TC_S1_182 - TC_S1_184 TC_S1_189, TC_S1_190 | Passed
| R017 | Admin should be able to view Trimester information. | TC_S1_001 TC_S1_017 - TC_S1_025 | Passed
| R018 | Admin should be able to add Trimester information. | TC_S1_002 - TC_S1_008 | Passed
| R019 | Admin should be able to edit Trimester information. | TC_S1_009 - TC_S1_013 | Passed
| R020 | Admin should be able to delete Trimester information. | TC_S1_014 - TC_S1_016 TC_S1_026 - TC_S1_028 | Passed
Sprint 2 | R021 | Admin should be able to view all assignments/exam's LOs. | TC_S2_090, TC_S2_093 | Passed
| R022 | Admin should be able to view all assignments/exam's LOs by filtering course’s name. | TC_S2_056 - TC_S2_060 | Passed
| R023 | Admin should be able to add new assignments/exam's LOs for tutor. | TC_S2_042 - TC_S2_047 | Passed
| R024 | Admin should be able to update new assignments/exam's LOs for tutor. | TC_S2_049 - TC_S2_052 | Passed
| R025 | Admin should be able to delete new assignments/exam's LOs for tutor. | TC_S2_053 - TC_S2_055 | Passed
| R026 | Admin should be able to release results of assignments/exam's LOs to students. | TC_S2_066 - TC_S2_079 | Passed
| R027 | Admin should be able to update results of assignments/exam's LOs that were released to students. | TC_S2_080, TC_S2_095, | Passed
| R028 | Admin should be able to delete results of assignments/exam's LOs that were released to students. | TC_S2_092 | Passed
| R029 | Admin should be able to set the retake of the failed assignments/exam's LOs to students. | TC_S2_094, TC_S2_096, TC_S2_097 | Passed
| R030 | Admin should be able to update results of assignments/exam's LOs to students who attended retake. | TC_S2_098, TC_S2_099 | Passed
Sprint 3 | R031 | Tutor should be able to add new student information. | TC_S3_052, TC_S3_059 | Passed
| R032 | Tutor should be able to delete student information. | TC_S3_060 | Passed
| R033 | Tutor should be able to view course information. | TC_S3_035, TC_S3_003, TC_S3_004 - TC_S3_007 | Passed
| R034 | Tutor should be able to view student information. | TC_S3_056, TC_S3_058, TC_S3_008 | Passed
| R035 | Tutor should be able to view all their assignments/exam's LOs. | TC_S3_039 | Passed
| R036 | Tutor should be able to view all their assignments/exam's LOs by filtering their course’s name. | TC_S3_036, TC_S3_037 | Passed
| R037 | Tutor should be able to add new assignments/exam's LOs for tutor. | TC_S3_044, TC_S3_045 | Passed
| R038 | Tutor should be able to update new assignments/exam's LOs for tutor. | TC_S3_046, TC_S3_047, TC_S3_075 | Passed
| R039 | Tutor should be able to delete new assignments/exam's LOs for tutor. | TC_S3_048, TC_S3_081 | Passed
| R040 | Tutor should be able to release results of their assignments/exam's LOs to students. | TC_S3_021, TC_S3_022, TC_S3_032 | Passed
| R041 | Tutor should be able to update results of their assignments/exam's LOs that were released to students. | TC_S3_010 - TC_S3_014 | Passed
| R042 | Tutor should be able to delete results of their assignments/exam's LOs that were released to students. | TC_S3_033 | Passed
| R043 | Tutor should be able to set the retake of failed assignments/exam's LOs to his students. | TC_S3_024, TC_S3_025 | Passed
| R044 | Tutor should be able to update the results of their assignments/exam's LOs to students who attended retake. | TC_S3_026 - TC_S3_030 | Passed
Sprint 4 | R045 | Admin should be able to login to the LOTA system. | TC_S4_048 | Passed
| R046 | Admin should be able to log out of the LOTA system. | TC_S4_064 | Passed
| R047 | Tutor should be able to login to the LOTA system. | TC_S4_047 | Passed
| R048 | Tutor should be able to log out of the LOTA system. | TC_S4_063 | Passed
| R049 | Student should be able to login to the LOTA system. | TC_S4_046 | Passed
| R050 | Student should be able to log out of the LOTA system. | TC_S4_062 | Passed
| R051 | Student should be able to view their results of assignments/exam's LOs. | TC_S4_003 | Passed
| R052 | Admin should be able to update their login password. | TC_S4_033 - TC_S4_045 | Passed
| R053 | Tutor should be able to update their login password. | TC_S4_020 - TC_S4_032 | Passed
| R054 | Student should be able to update their login password. | TC_S4_006 - TC_S4_019 | Passed