## Week#1
Question | Person | Week 1 : 9/9/24 ~ 13/9/24
|  | Mon | Tue | Wed | Thur | Fri
What did you do yesterday? | Bowang | – | – | – | Login function Register function | Customer details edit function Searching & Sorting function
| Diljot | – | – | – | Create test plan | -
| Frances | – | – | – | Create user stories | Review test plan
What will you work on today? | Bowang | – | – | Login function Register function | Customer details edit function Searching & Sorting function | Products displaying View product details function
| Diljot | – | – | Create test plan | Finished | -
| Frances | – | – | Create user stories | Review test plan | Finished
Do you have any obstacles? | Bowang | – | – | – | – | –
| Diljot | – | – | – | – | –
| Frances | – | – | – | – | –
Sprint Summary
This sprint has been productive and efficient, with the developer completing most of the key features. The tester has finalized the test plan based on user stories. There are no current obstacles.
Sprint Review
The sprint is progressing well, with essential features delivered by the developer. The project manager has completed all the necessary user stories. The tester, supported by a detailed test plan, is ready to begin testing. The sprint is moving forward efficiently, the team is on track.

## Week#2
Question | Person | Week 2 : 16/9/24 ~ 20/9/24
|  | Mon | Tue | Wed | Thur | Fri
What did you do yesterday? | Bowang | Products displaying View product details function | – | Unit testing for product and customer features SQL Server DB | Transaction view feature | Transaction delete feature
| Diljot | – | – | BBT (partially) | BBT (partially) | –
| Frances | – | – | WBT | WBT | –
What will you work on today? | Bowang | Finished | Unit testing for product and customer features SQL Server DB | Transaction view feature | Transaction delete feature | Unit testing for transaction features
| Diljot | – | BBT (partially) | BBT (partially) | Finished | –
| Frances | – | WBT | WBT | Finished | –
Do you have any obstacles? | Bowang | – | – | – | – | –
| Diljot | – | – | – | – | –
| Frances | – | – | – | – | –
Sprint Summary
This sprint is also productive, with the developer completing the rest of features and unit testing. The tester has finalized the black-box testing of login, register, sort, and transaction. Project manager has finished white-box testing. There are no current obstacles.
Sprint Review
The sprint is progressing well and smoothly, with all features and unit testing delivered by the developer. The project manager has completed white-box testing and the coverage rate is 100%. The tester finished black-box testing partially. The sprint is moving forward efficiently, everything is on track.

## Week#3
Question | Person | Week 3 : 23/9/24 ~ 27/9/24
|  | Mon | Tue | Wed | Thur | Fri
What did you do yesterday? | Bowang | Unit testing for transaction features | – | Automation testing (Selenium) | – | –
| Diljot | – | – | BBT, JMeter | – | –
| Frances | – | – | Automation testing (Selenium) | ERD (from sketch to image) Presentation slides (partially) | –
What will you work on today? | Bowang | Finished | Automation testing (Selenium) | Finished | – | –
| Diljot | – | BBT, Jmeter (on Home page) | Finished | – | –
| Frances | – | Automation testing (Selenium) | ERD (from sketch to image) Presentation slides (partially) | Finished | –
Do you have any obstacles? | Bowang | – | – | – | – | –
| Diljot | – | Cannot find Jmeter.bat | – | – | –
| Frances | – | – | – | – | –
Sprint Summary
A productive sprint, black-box testing was finished. Automation testing was performed by using Selenium. And we turned the rough sketch on paper into a more visually appealing image. One obstacle was that Jmeter.bat could not be found when using JMeter to perform the performance and load test, but it was solved at last by asking help from the tutor (the lab's cumputer needs admin access).
Sprint Review
The sprint is progressing well. BBT, performance and load test, and automation testing are all completed. The team moves forward to the last sprint.

## Week#4
Question | Person | Week 4 : 30/9/24 ~ 4/10/24
|  | Mon | Tue | Wed | Thur | Fri
What did you do yesterday? | Bowang | – | – | Puma Scan | Security document | –
| Diljot | – | – | Jmeter (on controllers) | – | –
| Frances | – | – | Puma Scan | Security document | Presentation slides
What will you work on today? | Bowang | – | Puma Scan | Security document | Finished | –
| Diljot | – | Jmeter (on controllers) | Finished | – | –
| Frances | – | Puma Scan | Security document | Presentation slides | Finished
Do you have any obstacles? | Bowang | – | – | – | – | –
| Diljot | – | – | – | – | –
| Frances | – | – | – | – | –
Sprint Summary
In this sprint, tester did more tests on controllers using Jmeter. Programmer and project manager finished the Static Code Analysis and the related security document.
Sprint Review
The sprint is progressing well. Performance and load test and Static Code Analysis are all completed. All required testing processes are finished by the end the this last sprint.